## VaultNote Threat Model
Severity | Likelihood | Impact | STRIDE | Function | CWE | Risk Category | Technical Asset | Communication Link | RAA % | Identified Risk | Action | Mitigation | Check | ID | Status | Justification | Date | Checked by | Ticket
Elevated | Likely | High | Information Disclosure | Architecture | CWE-319 | Data Disclosure - Personal Data Transmitted Over Unencrypted Channel | API Server |  | 82 | Data Disclosure: API Server processes personal data and has an unencrypted outgoing communication link | Encrypt all links that carry personal data | Migrate all communication links carrying PII data assets to TLS 1.2+ (preferably TLS 1.3). For internal service-to-service communication, consider mutual TLS (mTLS). | Are all communication links carrying personal data encrypted in transit? | data-disclosure-pii-unencrypted-link@api-server | In Progress | The API server communicates with PostgreSQL, Redis, and MinIO over plaintext connections within backend-net. TLS for all internal database connections is planned post-launch in VAULT-117. MinIO credential rotation is tracked in VAULT-110 (blocker). | 2026-04-25 | Security Team | VAULT-117
Elevated | Likely | High | Information Disclosure | Architecture | CWE-319 | Data Disclosure - Personal Data Transmitted Over Unencrypted Channel | Nginx Reverse Proxy |  | 2 | Data Disclosure: Nginx Reverse Proxy processes personal data and has an unencrypted outgoing communication link | Encrypt all links that carry personal data | Migrate all communication links carrying PII data assets to TLS 1.2+ (preferably TLS 1.3). For internal service-to-service communication, consider mutual TLS (mTLS). | Are all communication links carrying personal data encrypted in transit? | data-disclosure-pii-unencrypted-link@nginx-proxy | In Progress | Duplicate of VAULT-102 (Nginx→API plaintext link). Resolved when mTLS migration completes in sprint 22. LINDDUN data-disclosure finding is tracked under the same remediation work. | 2026-04-18 | Security Team | VAULT-102
Elevated | Likely | Medium | Repudiation | Operations | CWE-778 | Detectability - PII Flows Without Audit Logging | Nginx Reverse Proxy |  | 2 | Detectability: Nginx Reverse Proxy processes PII and has communication links without audit logging | Enable audit logging on all links carrying personal data | Set audit_logged to true on every communication link that transmits PII data assets. Store logs in a tamper-evident system separate from the application. | Are all communication links that carry personal data audit-logged? | detecting-no-audit-logging@nginx-proxy | Accepted | Nginx access.log captures all incoming requests (IP, URL, status code, response size). Individual API-level audit events are handled by the API server. The Nginx→API internal hop has no separate audit log; this is accepted as the TLS-termination boundary log is sufficient for DMZ-level audit requirements. | 2026-04-25 | Security Team | VAULT-115
Elevated | Likely | Medium | Repudiation | Operations | CWE-778 | Detectability - PII Flows Without Audit Logging | API Server |  | 82 | Detectability: API Server processes PII and has communication links without audit logging | Enable audit logging on all links carrying personal data | Set audit_logged to true on every communication link that transmits PII data assets. Store logs in a tamper-evident system separate from the application. | Are all communication links that carry personal data audit-logged? | detecting-no-audit-logging@api-server | In Progress | Structured request/response audit logging (Morgan + Winston) is implemented for authenticated endpoints but coverage is incomplete for internal data-access events. Full audit trail covering all PII-processing operations is tracked in VAULT-116. Target: sprint 23. | 2026-04-25 | Security Team | VAULT-116
Elevated | Likely | Medium | Information Disclosure | Development | CWE-922 | Non-Repudiation - PII or Auth Tokens Accessible in Browser-Side Storage | Browser SPA |  | 54 | PII in Client-Side Storage: browser asset Browser SPA processes personal data that may be stored in JavaScript-accessible browser storage | Move session tokens to HttpOnly cookies; apply Content-Security-Policy | Replace localStorage/sessionStorage token storage with HttpOnly, Secure, SameSite=Strict cookies. Cookies with the HttpOnly flag are inaccessible to JavaScript, eliminating the XSS token-theft vector. Deploy a strict Content-Security-Policy to limit damage from any residual XSS. Tag the asset has-httponly-session once deployed. | Are authentication tokens stored in HttpOnly cookies rather than localStorage? Is a Content-Security-Policy header present on all pages served to this browser client? | pii-client-side-storage@browser-spa | Unchecked
Elevated | Likely | Medium | Information Disclosure | Architecture | CWE-359 | Unawareness - PII Processed Without a Consent Management Component | Browser SPA |  | 54 | Unawareness: Browser SPA processes end-user PII but no consent management component is present | Add a consent management technical asset to the architecture | Introduce a consent-manager (tagged with technology consent-manager) to capture, store, and honour data-subject preferences. | Does the architecture include a consent management component when processing PII? | unawareness-no-consent-technology@browser-spa | In Progress | A consent management platform (CMP) is being evaluated (OneTrust / Osano). In the interim, the privacy policy is displayed at registration and users explicitly accept terms before account creation. Formal CMP integration is planned for Q3 2026. | 2026-04-25 | Privacy Team | VAULT-118
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-359 | Linkability - Same PII Data Asset Processed Across Multiple Trust Boundaries | API Server |  | 82 | Linkability: API Server processes a PII data asset also flowing into another trust boundary | Apply data minimisation and per-context pseudonymisation | Use per-context pseudonyms or pairwise identifiers so the same natural person cannot be linked across trust boundaries. | Does each PII data asset appear in assets across more than one trust boundary? | linking-pii-multi-boundary@api-server | Accepted | The API server bridges frontend-net and backend-net by architectural necessity — it is the sole legitimate data path between the two networks. Cross-boundary PII flow is an inherent design characteristic, not a misconfiguration. Mitigated by authentication + authorization enforcement at the API layer. | 2026-04-25 | Security Team | VAULT-119
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-359 | Linkability - Same PII Data Asset Processed Across Multiple Trust Boundaries | Browser SPA |  | 54 | Linkability: Browser SPA processes a PII data asset also flowing into another trust boundary | Apply data minimisation and per-context pseudonymisation | Use per-context pseudonyms or pairwise identifiers so the same natural person cannot be linked across trust boundaries. | Does each PII data asset appear in assets across more than one trust boundary? | linking-pii-multi-boundary@browser-spa | Accepted | The Browser SPA processes user-credentials and note-content across the Internet and DMZ boundaries by design (user-facing client). The risk is inherent to the SPA architecture; mitigated by HTTPS-only transport and short-lived session tokens. | 2026-04-25 | Security Team | VAULT-119
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-359 | Linkability - Same PII Data Asset Processed Across Multiple Trust Boundaries | MinIO Object Storage |  | 39 | Linkability: MinIO Object Storage processes a PII data asset also flowing into another trust boundary | Apply data minimisation and per-context pseudonymisation | Use per-context pseudonyms or pairwise identifiers so the same natural person cannot be linked across trust boundaries. | Does each PII data asset appear in assets across more than one trust boundary? | linking-pii-multi-boundary@minio-storage | Accepted | File attachments uploaded via the Internet are stored in the Data Tier. Cross-boundary flow is by design. VAULT-110 (credential rotation + SSE) addresses the high-severity storage risk; the linkability finding is accepted as an inherent architectural property. | 2026-04-25 | Security Team | VAULT-119
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-359 | Linkability - Same PII Data Asset Processed Across Multiple Trust Boundaries | Nginx Reverse Proxy |  | 2 | Linkability: Nginx Reverse Proxy processes a PII data asset also flowing into another trust boundary | Apply data minimisation and per-context pseudonymisation | Use per-context pseudonyms or pairwise identifiers so the same natural person cannot be linked across trust boundaries. | Does each PII data asset appear in assets across more than one trust boundary? | linking-pii-multi-boundary@nginx-proxy | Accepted | Nginx is the TLS-termination proxy and must bridge Internet and DMZ by design. Cross-boundary PII flow is intentional and unavoidable for this component. | 2026-04-25 | Security Team | VAULT-119
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-359 | Linkability - Same PII Data Asset Processed Across Multiple Trust Boundaries | PostgreSQL Database |  | 100 | Linkability: PostgreSQL Database processes a PII data asset also flowing into another trust boundary | Apply data minimisation and per-context pseudonymisation | Use per-context pseudonyms or pairwise identifiers so the same natural person cannot be linked across trust boundaries. | Does each PII data asset appear in assets across more than one trust boundary? | linking-pii-multi-boundary@postgresql-db | Accepted | PostgreSQL stores credentials and note content that originate from multiple trust boundaries (Internet → DMZ → App Network → Data Tier). This is inherent to the data flow by design. Risk is accepted; mitigated by parameterized queries and authentication-only access via the API. | 2026-04-25 | Security Team | VAULT-119
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-359 | Linkability - Same PII Data Asset Processed Across Multiple Trust Boundaries | Redis Cache |  | 40 | Linkability: Redis Cache processes a PII data asset also flowing into another trust boundary | Apply data minimisation and per-context pseudonymisation | Use per-context pseudonyms or pairwise identifiers so the same natural person cannot be linked across trust boundaries. | Does each PII data asset appear in assets across more than one trust boundary? | linking-pii-multi-boundary@redis-cache | Accepted | Session identifiers originate from users across the Internet boundary. Storage in Redis within the Data Tier is unavoidable. Mitigated by short TTL (15 minutes), revocation list, and password-protected access. | 2026-04-25 | Security Team | VAULT-119